## Product Backlog
🏦 KidBank — Product Backlog ¦ SE-25 Midterm ¦ Polito.uz 2026
Agile / Scrum • JavaFX • JSON Storage • JUnit ¦ Deadline: 29 March 2026 (Backlog) & 10 May 2026 (Final)
ID | Epic | Role | User Story | Acceptance Criteria | Priority | SP | Iter | MoSCoW | Status | Notes
US01 | Auth | Parent | Tizimga ota-ona sifatida ro'yxatdan o'tmoqchiman | Email+parol kiritiladi; JSON ga saqlanadi; xato bo'lsa xabar | High | 3 | 1 | Must Have | To Do | users.json
US02 | Auth | Child | Tizimga bola sifatida kirishni xohlayman | Username+parol tekshiriladi; xato xabar; dashboard ochiladi | High | 2 | 1 | Must Have | To Do | Session
US03 | Auth | Parent | Bolani profilimga bog'lashni xohlayman | Bola ID kiritiladi; bog'liq bo'lsa xato; ro'yxatda ko'rinadi | High | 3 | 1 | Must Have | To Do | 1 ota → ko'p bola
US04 | Account | Child | Joriy balansimni ko'rishni xohlayman | Dashboard da balans karta; har tranzaksiyadan so'ng yangilanadi | High | 2 | 1 | Must Have | To Do | Real-time
US05 | Account | Child | Jamg'arma hisob ochmoqchiman | Hisob nomi + maqsad summa; current dan ajralgan holda | Medium | 3 | 2 | Should Have | To Do | Bir necha hisob
US06 | Account | Child | Hisoblar orasida pul o'tkazmoqchiman | Summa kiritiladi; balans tekshiriladi; tarixga yoziladi | Medium | 3 | 2 | Should Have | To Do | Overdraft yo'q
US07 | Tasks | Parent | Bola uchun yangi vazifa qo'shmoqchiman | Nom, tavsif, mukofot, deadline; tasks.json ga saqlanadi | High | 3 | 1 | Must Have | To Do | Mukofot > 0
US08 | Tasks | Child | Menga berilgan vazifalarni ko'rishni xohlayman | Kartochka ko'rinishi; status badge; mukofot summasi ko'rinadi | High | 2 | 1 | Must Have | To Do | Status filter
US09 | Tasks | Child | Vazifani bajardim deb belgilashni xohlayman | Status → 'Tasdiq kutilmoqda'; ota-onaga ko'rinadi | High | 2 | 1 | Must Have | To Do | Bir marta
US10 | Tasks | Parent | Bolaning vazifasini tasdiqlash yoki rad etishni xohlayman | Tasdiq → pul o'tadi; Rad → status qaytadi; xabar yuboriladi | High | 3 | 1 | Must Have | To Do | Auto tranzaksiya
US11 | Tasks | Parent | Vazifani tahrirlash yoki o'chirishni xohlayman | Faqat ota-ona; 'Kutilmoqda' holatidagilarni o'chirish mumkin emas | Low | 2 | 3 | Could Have | To Do | Ogohlantirish
US12 | Wallet | Child | Pulimni yechib olmoqchiman | Summa kiritiladi; balans tekshiriladi; transactions.json ga | High | 3 | 2 | Must Have | To Do | Balans >= 0
US13 | Wallet | Child | Kirim-chiqim tarixini ko'rishni xohlayman | Sana, tur, summa, sabab; haftalik/oylik filter | Medium | 3 | 2 | Should Have | To Do | Eng yangi avval
US14 | Wallet | Parent | Bolaga qo'shimcha pul bermoqchiman | Summa + sabab; bolaning balansi yangilanadi; 'Bonus' turi | Medium | 2 | 2 | Should Have | To Do | Limit belgilash
US15 | Savings | Child | Yangi jamg'arma maqsad qo'ymoqchiman | Nom, summa, deadline; progress 0%; goals.json ga | High | 3 | 2 | Must Have | To Do | Ko'p maqsad
US16 | Savings | Child | Maqsadga qancha qolganini bilmoqchiman | Progress bar %; qolgan summa; necha vazifa kerak hisob | Medium | 2 | 2 | Should Have | To Do | Formula: qolgan/o'rtacha
US17 | Savings | Child | Maqsad hisobiga pul yo'naltirishni xohlayman | Joriy hisobdan ayiriladi; maqsad hisobiga qo'shiladi | Medium | 3 | 3 | Should Have | To Do | 2 tranzaksiya
US18 | Spending | Child | Xarajat rejasi kiritmoqchiman | Nom, kategoriya, summa, sana; spending.json ga | Medium | 3 | 2 | Should Have | To Do | Kategoriyalar
US19 | Spending | Child | Balansim yetarlimi bilmoqchiman | Yashil 'Yetarli' / Qizil 'Yetarli emas'; necha vazifa kerak | Medium | 2 | 2 | Should Have | To Do | Real-time
US20 | Spending | Child | Necha vazifa bajarishim kerakligini bilmoqchiman | O'rtacha mukofot hisobi; kerakli vazifalar soni | Low | 2 | 3 | Could Have | To Do | 0 vazifa → N/A
US21 | Reports | Parent | Bolaning haftalik hisobotini ko'rishni xohlayman | Bar chart: ishlagan vs sarflagan; top-3 vazifa; muddat filtri | Low | 4 | 3 | Could Have | To Do | JavaFX BarChart
US22 | Reports | Child | O'zimning statistikamni ko'rishni xohlayman | Jami ishlagan; jami sarflagan; aktiv maqsadlar; top vazifa | Low | 3 | 3 | Could Have | To Do | Dashboard widget
JAMI: 22 ta User Story ¦ High: COUNTIF quyida |  |  |  |  | 10 | 0

## Sprint Planning
🗓️ Sprint Planning & Iteration Details
Iteration | Muddat | US IDs | Story Points | Fokus Sohasi | Natija | Asosiy Vazifalar | Status
Iteration 1 | 1–10 April 2026 | US01–US10 | ~23 SP | Auth, Tasks, Dashboard | Working Software v1 | Login/Register (JSON), Parent+Child dashboard, Vazifa CRUD, Balans ko'rsatish, JsonStorage | In Progress
Iteration 2 | 13–17 April 2026 | US11–US19 | ~23 SP | Wallet, Savings, Spending | Working Software v2 | Deposit/Withdraw, Tranzaksiya tarixi, Jamg'arma maqsad, Spending plan, Demo 2 | To Do
📋 Daily Standup — Scrum 3 Soruvi
1 | Kecha nima qildim? | Bajarilgan tasklar haqida qisqacha
2 | Bugun nima qilaman? | Bugungi rejalashtirilgan vazifalar
3 | Qandaydir to'siq bormi? | Blocker → Scrum Master hal qiladi
✅ Definition of Done (Vazifa qachon 'Tayyor' hisoblanadi)
1 | Kod yozildi | Java kodi IntelliJ da ishlaydi, compile xatosi yo'q
2 | JUnit test | Har service uchun kamida 1 ta JUnit test yozildi
3 | JavaDoc | Barcha public methodlarda /** */ komment mavjud
4 | Code Review | Kamida 1 guruh a'zosi kodingizni ko'rib chiqdi
5 | JSON ishlaydi | Saqlash/yuklash JSON fayllar bilan to'g'ri ishlaydi
6 | Error handling | Xato inputlarda tushunarli xabar ko'rsatiladi

## Roadmap
🗺️ Agile Roadmap — KidBank (Feb – May 2026)
Hafta / Sana | Faoliyat | Natija | Mas'ul | Deadline | Holat | Eslatma
16–20 Feb 2026 | Guruh tuzish, rol taqsimlash, PDF o'qish va muhokama | Guruh shartnomasi, rollar jadvali | Barcha | 20 Feb | ✅ Done | Scrum Master tanlash
23 Feb – 13 Mar | Talablarni yig'ish, User Story yozish, Product Backlog | Product Backlog (Excel fayl) | PO + Jamoa | 13 Mar | ✅ Done | Story writing workshop
16–27 Mar | Figma prototip chizish, Demo 1, foydalanuvchi fikri | Prototype PDF + Demo 1 feedback | Dizayner | 27 Mar | 🔄 Jarayonda | Low/mid fidelity yetarli
⚠️ 29 Mar — DEADLINE | 1-CHI TOPSHIRIQ: Backlog + Prototip | Productbacklog_groupXXX.xlsx + Prototype_groupXXX.pdf | Guruh Lideri | 29 Mar | 📌 DEADLINE | Email: sherzod.haydarov@polito.uz
1–10 Apr 2026 | Iteration 1: Login, register, vazifa, balans, JSON | Working Software v1 | Dev Jamoasi | 10 Apr | ⏳ Kelgusi | Core funksiyalar
13–17 Apr 2026 | Iteration 2: Hamyon, tarix, jamg'arma, spending + Demo 2 | Working Software v2 + Demo 2 | Dev Jamoasi | 17 Apr | ⏳ Kelgusi | Demo 2 — professor feedback
20–24 Apr 2026 | Iteration 3: Hisobot, UI, JUnit testlar, JavaDocs | Working Software v3 | Dev Jamoasi | 24 Apr | ⏳ Kelgusi | TDD, JavaDocs
27 Apr – 8 May | README, User Manual, ZIP tayyorlash, final test | Final ZIP + Report PDF | Barcha | 8 May | ⏳ Kelgusi | Max 25 bet report
⚠️ 10 May — DEADLINE | YAKUNIY TOPSHIRIQ: Report + Software | Report_groupXXX.pdf + Software_groupXXX.zip | Guruh Lideri | 10 May | 📌 DEADLINE | Email topshiriq
11–16 May 2026 | Formal Demo — professor oldida namoyish + savol-javob | Muvaffaqiyatli demo | BARCHA ⚠️ | 16 May | 📌 DEMO | Barcha a'zolar SHART

## Figma TZ
🎨 Figma Texnik Topshirig'i (Design Specification) — KidBank
🖌️ Design System — Rang, Font, Komponent Spesifikatsiyalari
Kategoriya | Qiymat | Hex / Raqam | Qo'llanilishi | Eslatma
Primary Color | Royal Blue | #1A3FD4 | Tugmalar, headerlar, asosiy elementlar | Main brand color
Accent Color | Neon Green | #39FF14 | Highlight, progress bar, success | Sparingly ishlatilsin
Background | Pure White | #FFFFFF | Barcha ekranlar foni | Clean base
Text Primary | Near Black | #1A1A1A | Sarlavha va asosiy matn | High contrast
Text Secondary | Gray | #666666 | Tavsif, caption, label | Secondary info
Error | Red | #D32F2F | Xato holati, 'yetarli emas' | Destructive
Success | Green | #388E3C | 'Yetarli', tasdiqlangan holat | Positive
Border Radius | Kartochka: 12px | Tugma: 24px, Input: 8px | Barcha komponentlar | Consistent rounding
Font Family | Inter yoki Nunito | Google Fonts | Barcha matnlar | Clean modern
Font Sizes | H1: 28px Bold | H2:22px ¦ Body:14px ¦ Caption:12px | Tipografiya ierarxiyasi | 8pt grid
Grid / Spacing | 8px base grid | Sahifa padding: 24px ¦ Card: 16px | Layout tizimi | Consistent
Frame Size | 1440 x 900 px | Desktop (Laptop screen) | Barcha Figma frame-lar | Landscape
Shadow | 0 2px 12px | rgba(0,0,0,0.08) | Kartochka shadow | Subtle depth
Animation | 200ms | ease-in-out | Hover, focus state | Smooth
📱 Ekranlar Spesifikatsiyasi (11 ta ekran)
# | Ekran Nomi | Rol | UI Elementlar | Funksiya | Komponentlar (Java) | Eslatma
1 | Splash Screen | Hammaga | Logo, app nomi, tagline, loading | 3 sek → Login auto-redirect | AnimatedLogo, Timeline | Fade-in animatsiya
2 | Login | Hammaga | Email/username, parol (toggle), Kirish btn, xato label | Validatsiya → AuthService → Dashboard | TextField, PasswordField, Button | Rol avtomatik
3 | Register | Hammaga | Ism, email, parol x2, rol dropdown, parentID (bola uchun) | JSON validation → users.json → Login | ComboBox, TextField | ParentID faqat Child uchun
4 | Parent Dashboard | Parent | Greeting, bolalar cards, pending badge, stats, navbar | Bola kartasi → profil; Vazifa qo'sh → modal | DashboardCard, NavBar, Badge | Bottom nav: 3 tab
5 | Child Dashboard | Child | Balans hero card, aktiv vazifalar, progress bars, so'ngi 3 tx | Balans → Hamyon; Vazifa → Tasks | BalanceCard, ProgressBar, MiniList | Rangli hero card
6 | Vazifalar (Parent) | Parent | Jadval: nom/mukofot/status/sana, Yangi FAB, filter tabs | Tasdiq/Rad → BankService; Yangi → Modal | TableView, FAButton, TabBar | Pending badge
7 | Vazifalar (Child) | Child | Task card-lar: nom/tavsif/mukofot/deadline/status, Bajardim btn | Bajardim → Pending → ota-onaga | TaskCard, StatusBadge, ActionButton | Bajarilgan = kulrang
8 | Hamyon | Child | Balans top, filter tabs, tx list: sana/tur/summa/sabab | Filter → list yangilanadi | BalanceHeader, FilterTabs, TxList | Kirim: +yashil, Chiqim: -qizil
9 | Jamg'arma | Child | Maqsad cards: nom/target/progress/deadline, Yangi btn, Yo'naltir | Progress animatsiyali; SavingsService | GoalCard, ProgressBar, Modal | 100% → konfetti
10 | Xarajat Rejasi | Child | Xarajat ro'yxati: nom/summa/kategoriya/sana, Qo'shish, holat banner | Holat: Yashil/Qizil + necha vazifa kerak | SpendingList, StatusBanner, Chip | Kategoriya chip rangli
11 | Hisobot (Parent) | Parent | Period selector, BarChart (ishlagan vs sarflagan), top-3, stats | Period o'zgarsa → chart yangilanadi | BarChart, PeriodPicker, StatCard | JavaFX BarChart
🤖 AI Dizayn Prompt (Midjourney / Firefly / Figma AI)
Desktop app UI for "KidBank" — kids virtual banking. Clean professional fintech aesthetic, NOT childish. Colors: royal blue #1A3FD4 primary, neon green #39FF14 accent, white background. Rounded cards 12px, Inter font, 8px grid. Screens: Login, Parent Dashboard, Child Dashboard (balance hero card), Task Manager (status badges), Wallet (transaction list), Savings Goals (progress bars), Spending Plan (affordability). Flat design, subtle shadows, no gradients, no cartoon. 1440x900px desktop frames. Dribbble-quality fintech. --style raw --v 6.1 --ar 16:9 --q 2 --chaos 0

## Agile Methods
⚙️ Agile / Scrum Metodologiyasi — KidBank Loyihasi
Agile Tushuncha | Ta'rif | KidBank da qo'llanilishi | Chastota | Mas'ul | Natija
Scrum | Iterativ rivojlantirish; qisqa sprintlar; doimiy feedback | 3 iteration (Apr 1–24); har biri working software beradi | Har 2 haftada | Barcha | Working Software vX
Product Backlog | Ustuvorligi bilan barcha talab va funksiyalar ro'yxati | 22 ta User Story; High/Medium/Low; Story Points bilan | Doimiy | Product Owner | Backlog.xlsx
Sprint Backlog | Joriy sprint da bajarilishi kerak bo'lgan vazifalar | Har iteration boshida US-lar tanlanadi | Har sprint | Dev Jamoasi | Bajarilgan US-lar
Daily Standup | Kunlik 15 daqiqa yig'ilish: kecha/bugun/blocker | 3 savol: Kecha? Bugun? To'siq? | Har kuni | Scrum Master | Blocker hal
Sprint Review | Iteration oxirida natijani demo qilish | Demo 1 (27 Mar), Demo 2 (17 Apr), Formal (May) | Har iteration | Barcha | Feedback
Retrospective | Nimani yaxshi/yaxshilash? Keyingiga takomil | 30 daqiqa muhokama; action items yoziladi | Har iteration | Scrum Master | Action items
User Story | Foydalanuvchi nuqtai nazaridan talablar | 22 ta US formatida (Kim/Nima/Nima uchun) | Requirements | Product Owner | Backlog
Story Points | Murakkablik nisbiy baholash (Fibonacci: 1,2,3,5,8) | 1=oddiy, 2=o'rta, 3=murakkab, 5=juda murakkab | Sprint planning | Dev Jamoasi | Capacity
MoSCoW | Must/Should/Could/Won't ustuvorlik usuli | Must Have=Sprint1-2; Could Have=Sprint3 | Backlog | PO | Scope
Definition of Done | Vazifa 'tayyor' deb hisoblash mezonlari | Kod+JUnit+JavaDoc+CodeReview+JSON+ErrorHandling | Har vazifa | Dev Jamoasi | Quality
Velocity | Har sprint bajarilgan Story Points | Target: ~23 SP/sprint; real velocity track | Har sprint | Scrum Master | Planning
Burndown Chart | Qolgan SP vaqt o'tishi bilan kamayish grafigi | SP vs Kunlar — sprint taraqqiyotini ko'rsatadi | Har kuni | Scrum Master | Visibility
👥 Scrum Team Rollari
Rol | Mas'uliyat | KidBank da | Kimga mos | Vositalar | Natija
Product Owner | Backlog boshqarish, prioritet, stakeholder | Backlog yaratish, US yozish, AC belgilash | Guruh lideri | Excel, PDF requirements | Product Backlog
Scrum Master | Jarayonni boshqarish, blocker hal, standup | Daily standup o'tkazish, sprint report | Tajribali a'zo | Trello, standup notes | Sprint Report
Developer (x2-3) | Kod yozish, JUnit, JavaDocs | JavaFX UI, Service classlar, JSON storage | Barcha a'zolar | IntelliJ, Git, JUnit 5 | Working Code
Designer | UI/UX prototip, Figma | Figma ekranlar, design system, prototype PDF | 1 a'zo | Figma, Google Fonts | Prototype PDF